## Revision
Design Test Report
Version: 1.0
Revision History
Date | Version | Description | Author
2022-08-01 | 1.0 | Initial Draft | Dorothy Kisoromoi

## Project Info
Design Test Report
Version: 1.0
Project Information
Project Name
Description
Issue Date: | 2022-08-01
Owner: | Dorothy Kisoromoi
Author: | Dorothy Kisoromoi
Location:
Reviewer information | Name | Department | Position
Approver information
Note on B13: Can add more reviewers
Note on B15: You can add more approvers here

## Content
Test Report
Test Cycle | Integration Test
EXECUTED | PASSED |  |  | 130
| FAILED |  |  | 0
| (Total) TESTS EXECUTED (PASSED + FAILED) |  |  |  | 130
PENDING |  |  |  |  | 0
IN PROGRESS |  |  |  |  | 0 |  |  | Defect fixed | Not fixed
BLOCKED |  |  |  |  | 0 |  |  | 22 | 0
(Sub-Total) TEST PLANNED |  |  |  |  | 130
(PENDING + IN PROGRESS + BLOCKED + TEST EXECUTED)
Functions | Description | % TCs Executed | % TCs Passed | TCs pending | Priority | Remarks | Number of defects | Defect fixed
New Customer | Check new Customer is created | 100% | 100% | 0 | High |  | 0 | 0
Edit Customer | Check Customer can be edited | 100% | 100% | 0 | High |  | 1 | 1
New Account | Check New account is added | 100% | 100% | 0 | High |  | 0 | 0
Edit Account | Check Account is edit | 100% | 100% | 0 | High |  | 2 | 2
Delete Account | Verify Account is delete | 100% | 100% | 0 | High |  | 2 | 1
Delete customer | Verify Customer is Deleted | 100% | 100% | 0 | High |  | 3 | 2
Fund Transfer | [6 empty] | 8 | 7
Mini Statement | Verify Ministatement is generated | 100% | 100% | 0 | High |  | 2 | 1
Customized Statement | Check Customized Statement is generated | 100% | 100% | 0 | High |  | 4 | 4
Defect ID | Bug description |  |  | Test Case ID | Priority | Severity | Open date | Status | Raised By | Tested on Version
| Steps to Reproduce | Expected Results | Actual Results
1 | 1) Click on Delete Account 2) Enter required fields 3) Submit | 1) A pop - up "Do you really want to delete this account?" | No confirmation message shown |  | Low | Low | 2022-07-25 | Closed
2 | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | 1) A pop up "Do you really want to delete this customer?" | No confirmation message shown |  | Low | Low | 2022-07-25 | Closed
3 | 1) Click on Edit Customer 2) Enter Customer id 3) Submit | 1)A pop - up "Customer does not exist" 2) Redirect to Delete customer | alert " You are not authorize to edit this account!" redirect to delete customer page |  | Low | Low | 2022-07-25 | Closed
4 | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer | alert " You are not authorize to delete this account!" redirect to delete customer page |  | Low | Low | 2022-07-25 | Closed
5 | 1) Execute the above test case 2) Refresh Fund Transfer detail page | Page should redirect to fund transfer page | Not redirecting to fund transfer page on clicking refresh button |  | Low | Low | 2022-07-25 | Closed
6 | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop - up " Account # does not exist" | 1) A pop up "You are not authorize to Transfer Funds from this account!!" |  | Medium | Low | 2022-07-25 | Closed
7 | 1) Cliick on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "You are not authorize to Transfer Funds from this account!!" | 1) A pop up "No details found for this account!!" |  | Medium | Low | 2022-07-25 | Closed
8 | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "Payers account No and Payees account No Must Not be Same!!!" | No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown |  | Medium | Low | 2022-07-25 | Closed
9 | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "Transfer Failed. Account Balance low!!" | 1) A pop up "You cant transfer your account balance is low" |  | Medium | Low | 2022-07-25 | Closed
10 | 1) Refresh Deposit detail Page | Page should redirect to Deposit Page | Not redirecting to deposit page on clicking refresh button |  | Medium | Low | 2022-07-25 | Closed
11 | 1)Click on Withdrawal 2) Enter all required fields 3) Submit | An Error message "Transaction failed account balance is low !!" | withdrawal done |  | Medium | Low | 2022-07-25 | Closed
12 | 1) Click on Customized statement 2) Enter all required fields 3) Submit | 1) pop - up "From date field should be lower than to date field" | 1) pop - up "No transaction details found" |  | Medium | Low | 2022-07-25 | Closed
13 | 1) Click on Balance enquiry 2) Enter wrong account number which is not associated with customer 3) Submit | Display alert message " You are not authorize to get Balance details of this account!! " | You can see balance of any account |  | Medium | Low | 2022-07-25 | Closed
14 | 1) Refresh Fund Transfer detail Page shown in above test case | Redirect to Fund Transfer input Page | Not redirecting and fund is transfer again |  | High | Medium | 2022-07-25 | Closed
15 | 1) Click on Fund Transfer 2) Enter wrong Payer account number which is not associated with customer 3) Submit | Display alert messsage "You are not authorize to Transfer Funds from this account!! " | Not displaying alert message and transfers the fund successful |  | High | Medium | 2022-07-25 | Closed
16 | 1) Click on Fund Transfer 2) Enter wrong Payer or Payees account number which is not available in database 3) Submit | Display alert messsage " Account ### does not exist!!! " | Display alert messsage " No details found for this accounts !!! " |  | High | Medium | 2022-07-25 | Closed
17 | 1) Click on Fund Transfer 2) Enter same Payer account number and Payees account number which is available in database 3) Submit | Display alert messsage " Payers account No and Payees account No Must Not be Same!!! " | No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown |  | High | Medium | 2022-07-25 | Closed
18 | 1) Click on Mini Statement 2) Enter all required fields 3) Submit | Display alert messsage " You are not authorize to generate statement of this Account!! " | Ministatement is generated for any account that exists in database |  | High | Medium | 2022-07-25 | Closed
19 | 1) Click on customize statement 2) Enter all required fields 3) Submit | Display alert messsage " You are not authorize to generate statement of this Account!! " | Customized statement is generated for any account that exists in database |  | High | Medium | 2022-07-25 | Closed
20 | 1) Click on customize statement 2) Enter all required fields 3) Submit | Display alert messsage " FromDate field should be lower than ToDate field!!" | Display alert messsage " No details found for this accounts !!! " |  | High | Medium | 2022-07-25 | Closed
21 | 1) Enter a value in Account Number Field in URL which is exist in database 2) Press Enter | A Success message with mini statement in the json format should be displayed | Json format fail |  | High | Medium | 2022-07-25 | Closed
22 | 1) Do not enter a value in account number in URL | An error in message "No Data " should be displayed in json format | Data is shown |  | High | Medium | 2022-07-25 | Closed